## Sheet1
New Practice or Acquisition Start-up Checklist:
Task # | Task | Department or Person Responsible | Days to Start Date | Target Completion Date | Date Done | Notes:
PHYSICIAN NEGOTIATION PHASE
1 | Information gathering phase | Admin/Manager | 120+
2 | A confidentiality agreement needs to be signed by the physician/s | Admin/Manager | 120+
3 | A conflict of interest agreement needs to be signed by the physician/s | Admin/Manager | 120+
4 | Conduct a proforma or value analysis (Where applicable) | Admin/Manager | 120+
5 | Contract preparation | Contracting | 120+
6 | Contract negotiation | Contracting | 120+
7 | Verify if a malpractice tail is applicable and who will be paying the cost if the malpractice insurance carrier is changing | Contracting | 120+
8 | Obtain final approvals on contract terms and complete contract | Contracting | 120+
9 | Physician contract is signed | Contracting | 120+
10 | Prompt physician to term their existing malpractice insurance if the insurance carrier is changing | Contracting | 120+
PHYSICIAN EMPLOYMENT & PRACTICE SET-UP (120 days out)
11 | Verify Corporation is already setup and establish a Trade Name/DBA | Legal/Attorney | 120
12 | Obtain a Tax ID/EIN if one is not already established | Legal/Attorney | 120
13 | Begin work on any acquisition/asset purchase agreement (Where Applicable) | Legal/Attorney | 120
14 | Address the custodianship of the medical records if records are to come with the provider/s | Legal/Attorney | 120
15 | Obtain an FMV appraisal of any assets through an independent 3rd party appraiser | Legal/Attorney | 120
16 | Review any new/existing leases and vendor contracts with an attorney or accountant as needed | Legal/Attorney | 120
17 | Obtain the providers old Tax ID if applicable to assist with credentialing | Admin/Manager | 120
18 | Business License Requested (If applicable to state, county, city) | Admin/Manager | 120
19 | Occupational License Requested (If applicable to state, county, city) | Admin/Manager | 120
20 | Review Use Tax and OPT/Head tax (If applicable to state, county, city) | Admin/Manager | 120
21 | Choose office space and execute a lease/purchase | Admin/Manager | 120
22 | Order Local Telephone and Fax Lines (phone numbers) | Communications | 120
23 | Consider any buildout requirements and any associated safety features that need to be added (Eye washes etc.) | Admin/Manager | 120
24 | Apply for DEA registration | Physician | 120
25 | Apply for a state medical license | Physician | 120
26 | Join local and state medical society (Or verify current membership) | Physician | 120
27 | Completion of all credentialing applications for the credentialing staff | Physician | 120
28 | Completion of all hospital privilege applications | Physician | 120
29 | Obtain a bank lock box for insurance payments | Accounting | 120
30 | Complete a review of any quality requirements that may be required | Admin/Manager | 120
31 | Complete a walkthrough of Computer, Phone, Fax, and Copier needs | Communications | 120
32 | Assess phone system setup needs - Phone tree, expandability, etc. | Communications | 120
33 | Assess and specific computer and software needs - Verify all are approved for use | Admin/Manager | 120
34 | Review the capital and operating budget | Admin/Manager | 120
CREDENTIALING (120+ days out from the provider start)
35 | Provide credentialing staff the anticipated start date and the completed credentialing information | Credentialing | 120+
36 | Submit all insurance payer applications (Both commercial and federal as applicable) and complete the providers CAQH | Credentialing | 120+
37 | Obtain and apply for CLIA certificate (This may be required for Medicaid participation) | Credentialing | 120+
38 | Submit all hospital privilege applications at least 4 months before the provider/s start date, verify that the physician goes to committee and privileges are granted prior to the start date | Credentialing | 120+
39 | Verify list of insurances to be credentialed with or if there are any others that need to be considered, ensure all are in process and maintain a list of payers | Credentialing | 120+
PRACTICE SET-UP (90 days out)
40 | Verify payroll system is setup | Accounting | 90
41 | Establish all accounting and reporting systems | Accounting | 90
42 | Establish all internal controls | Accounting | 90
43 | Setup business/property insurance | Admin/Manager | 90
44 | Establish communication between HR, Leadership, and any other departments | Admin/Manager | 90
45 | Identify the staffing plan for the clinic (# of positions, titles, etc.) | Admin/Manager | 90
46 | Advertise open positions with HR or the hiring manager (Online, practice job site, agency, or other sources) | HR | 90
47 | Consider any existing staff for the positions | HR | 90
48 | If existing staff are joining they should meet with admin/HR | HR | 90
49 | Establish and communicate hiring procedures, policies, and timelines | HR | 90
50 | Establish and communicate benefits | HR | 90
51 | Finalize data circuit and phone line needs | Communications | 90
52 | Finalize network connectivity requirements | Communications | 90
53 | Determine and finalize copier needs | Communications | 90
54 | Place order for computers and printers | Communications | 90
55 | Complete and finalize an assessment of the EMR to be utilized and purchase the software/licenses | Communications | 90
56 | Submit orders for any high dollar capital equipment needed (Medical or Office) | Admin/Manager | 90
57 | Design Patient registration form/consent form - Include all patient demographics | Admin/Manager | 90
58 | Design all HIPAA or other necessary forms | Admin/Manager | 90
59 | Hire Practice Manager | Admin/Manager | 90
60 | Staffing - Research compensation ranges, interview, check references, make offers & confirm start dates | HR | 90
61 | Design the practice logo | Admin/Manager | 90
PRACTICE SET-UP (60 days out)
62 | Setup provider/s in the EMR | Communications | 60
63 | Obtain schedules and build them in the EMR | Admin/Manager | 60
64 | Develop the encounter form/superbill of all of the CPT codes to be billed and used by the practice | Admin/Manager | 60
65 | Quote phone system and acquire | Communications | 60
66 | Finalize setup of phone plans for local/long distance calls | Communications | 60
67 | Request access to hospital based computer systems if applicable | Admin/Manager | 60
68 | Order cell phones and pagers as needed | Admin/Manager | 60
69 | Verify manager has all appropriate computer systems access | Admin/Manager | 60
70 | Submit all background check forms for providers and staff to HR | Admin/Manager | 60
71 | Order Fax and Copier | Communications | 60
72 | Order Data/Phone Circuit | Communications | 60
73 | Order ICD-10, CPT, HCPCS, PDR or any other necessary reference materials | Admin/Manager | 60
74 | Set up Answering Service | Admin/Manager | 60
75 | Set up Transcription or Scribe services if applicable | Admin/Manager | 60
76 | Complete a space design | Admin/Manager | 60
77 | Order Office Furniture | Admin/Manager | 60
78 | Order major medical Equipment & Exam Tables | Admin/Manager | 60
79 | Review any practice marketing needs at 60 days out | Marketing | 60
80 | Setup banking and order supplies | Accounting | 60
81 | Setup Merchant Card Account needs (Visa/MC, AMEX, Discover) | Accounting | 60
82 | Set up a cash drawer or change fund for patient payments | Accounting | 60
PRACTICE SET-UP (30 days out)
83 | Orient the practice manager on the billing operations | Admin/Manager | 30
84 | Establish billing and charge entry personnel (If applicable) | Admin/Manager | 30
85 | Set the daily and monthly reporting needs for the new practice | Admin/Manager | 30
86 | Determine where the billing and charge entry will occur | Admin/Manager | 30
87 | Schedule EMR training for the new office staff | Admin/Manager | 30
88 | Complete OSHA training | HR | 30
89 | Complete HIPAA training | Admin/Manager | 30
90 | Review any training and orientation materials and verify compliance requirements are in place | Admin/Manager | 30
91 | Confirm HR Policies and Procedures and compliance training is schedules to occur for all employees | HR | 30
92 | Schedule HR orientation with staff and providers prior to the start date | HR | 30
93 | Finalize start dates for all employees and complete any pending pre-screening (Background checks and drug screening etc.) | HR | 30
94 | Verify all phones and computer are working properly and that all data/phone circuits were installed | Communications | 30
95 | Verify the office phone number/s | Communications | 30
96 | Verify access for staff to any payroll systems as necessary | Admin/Manager | 30
97 | Create a payer resource manual and fee schedule cheat sheet for the front office staff | Admin/Manager | 30
98 | Implement a system or method for gathering patient satisfaction information | Admin/Manager | 30
99 | Verify all interior building and suite signage is ordered | Admin/Manager | 30
100 | Exterior signage - As applicable | Admin/Manager | 30
101 | Setup or update website - Add physician bio and other relevant information | Marketing | 30
102 | Contact medical society(ies) re: publications if applicable | Admin/Manager | 30
103 | Update blue/yellow book information | Admin/Manager | 30
104 | Notify and/or contact area physicians/referral sources | Marketing | 30
105 | Sign up with any patient referral services if applicable | Marketing | 30
106 | Schedule open house | Marketing | 30
107 | Notify post office of mail delivery | Admin/Manager | 30
108 | Create a marketing plan/budget and initiate setup of any marketing must to items | Marketing | 30
109 | Create press release | Marketing | 30
110 | Contact local publications (Newspapers, community association newsletters etc.) | Marketing | 30
111 | Order printing (Stationary, RX pads, and appointment cards) | Admin/Manager | 30
112 | Patient education materials (brochures, flyers, etc.) | Admin/Manager | 30
113 | Contact pharmaceutical reps | Admin/Manager | 30
114 | Setup any purchasing agreements (If applicable) | Admin/Manager | 30
115 | Setup interoffice courier (If applicable) | Admin/Manager | 30
116 | Determine in-office lab services to be performed, and verify CLIA waiver or certificate has been received | Admin/Manager | 30
117 | Finalize medical records system (Paper, electronic, & medical records) | Admin/Manager | 30
118 | Determine and finalize after hours coverage | Admin/Manager | 30
119 | Order subscriptions | Admin/Manager | 30
120 | Setup e-prescribe with your EMR vendor | Admin/Manager | 30
121 | Define on-call systems/procedures | Admin/Manager | 30
122 | Define daytime systems/procedures | Admin/Manager | 30
123 | Define prescription refill guidelines | Admin/Manager | 30
124 | Define telephone triage and prescription refill services | Admin/Manager | 30
125 | Determine referral requirements, design form, create written policy and procedures | Admin/Manager | 30
126 | Arrange for diagnostic services (lab/diagnostic tests) | Admin/Manager | 30
127 | Design Lab/DX Test Order Form | Admin/Manager | 30
128 | Define Pre-certification Procedures | Admin/Manager | 30
129 | Define Procedures for notifying patient of results | Admin/Manager | 30
130 | Medical supplies: Define needs, interview vendors & get pricing, arrange and place initial order and reordering | Admin/Manager | 30
131 | Verify and order pharmaceuticals for the practice (Please note there are special requirements for narcotics) | Admin/Manager | 30
132 | If sample medications will be kept in the practice, verify that all appropriate tracking systems are in place | Admin/Manager | 30
133 | Office supplies: Define needs, interview vendors & get pricing, arrange for initial orders and reorders | Admin/Manager | 30
134 | Order safety supplies as necessary - Including but not limited to outlet covers, AED, CPR masks, ambu bags, and a weather radio | Admin/Manager | 30
135 | Set up office (Install furniture, computer equipment, decorate office, organize printed materials, and hang pictures | Admin/Manager | 30
136 | Arrange deliveries: Waste management, office supplies, medical supplies, and laundry | Admin/Manager | 30
137 | Meet with hospital pharmacy director, if any drugs will be acquired from the hospital | Admin/Manager | 30
138 | Define no-show policies and procedures | Admin/Manager | 30
139 | Determine practice hours & scheduling protocol including hours, appointment types, and scheduling types | Admin/Manager | 30
140 | Work with the practice manager to determine appropriate scheduling of patients for the day of go live | Admin/Manager | 30
141 | Review with the manager the daily/weekly/monthly reporting requirements | Admin/Manager | 30
142 | Establish service with a paper shredding vendor and for fire extinguishers | Admin/Manager | 30
143 | Setup Biohazard waste services | Admin/Manager | 30
144 | Setup Linen/Laundry vendor as needed | Admin/Manager | 30
145 | If it is an acquired practice, verify all old vendors have been cancelled and have been switched to the new vendors | Admin/Manager | 30
146 | Determine current staff knowledge base in anticipation of necessary EMR training and levels of access needed | Admin/Manager | 30
147 | Complete a training session with the manager on credit card machine use and deposit protocols | Admin/Manager | 30
148 | Review required software applications / reports with the office manager and arrange training as appropriate | Admin/Manager | 30
TROUBLE-SHOOTING (1 week before)
149 | Coding and documentation training/review with the physician/s | Admin/Manager | 7
150 | Finalize revisions to superbill/encounter form and any diagnostic code lists | Admin/Manager | 7
151 | Post and compliance posters, patient posters, or any necessary policies and procedures | HR | 7
152 | New hires go to HR to complete any new hire paperwork and obtain a badge | HR | 7
153 | Complete any mandatory orientation or onboarding training | HR | 7
154 | Poster labor regs poster, OSHA, and anything else required by your state or city | HR | 7
155 | Have notice of privacy practice brochures or printouts available | Admin/Manager | 7
156 | Post any necessary copyright notices | Admin/Manager | 7
157 | Verify all computers/data lines, printers, phones/lines, and copiers are functioning properly | Communications | 7
158 | Verify staff has access to the timeclock or payroll system as applicable | Admin/Manager | 7
159 | Obtain a list of all participating insurances for the providers | Credentialing | 7
160 | Verify if any additional office/medical supplies are needed | Admin/Manager | 7
161 | Verify with answering service and transcription vendors that they are ready for go live | Communications | 7
162 | Complete any final operational training for the staff (Job functions, coding, etc.) | Admin/Manager | 7
FIRST DAY OF PRACTICE
163 | Have information technology support available in case of any computer, network, or phone issues | Communications | 0
164 | Copy/scan insurance cards. Gather all patient demographic, consent, and HIPAA forms and enter them into the EMR | Admin/Manager | 0
165 | Do daily deposits and credit card machine reconciliation | Admin/Manager | 0
166 | If paper superbills/encounter forms have been used, verify that they contain all patient demographics, account number, CPT codes, ICD-10 codes, and the physicians signature/date | Admin/Manager | 0
167 | Train staff: HIPAA, OSHA, employee procedures, scheduling, billing, & referral procedures | Admin/Manager | 0
168 | Coordinate with your billing company and staff on charge entry and billing | Admin/Manager | 0
169 | Setup service with a medical records copier service (If necessary) | Admin/Manager | 0
30 DAYS POST GO LIVE (+30 days)
170 | Have medical records audited to verify completeness and accuracy | Admin/Manager | +30
171 | Verify all staff training and orientation was completed | Admin/Manager | +30
172 | Verify payments from insurance payers match contracted rates | Admin/Manager | +30
173 | Monitor patient flow and look for opportunities for improvement | Admin/Manager | +30